# WS-DPS: DATA PRIVACY / SECURITY / GOVERNANCE

# Draft Deliverables for Meeting 4 Convergence Gate

Prepared by Jillian Burkley for John Black

FCCPS AI in Schools Ad Hoc Advisory Committee

February 2026 — DRAFT v0.1 for Co-Lead Review

# Purpose of This Document

This package includes draft versions of all three WS-DPS deliverables required for the March 6 convergence gate, along with the readiness checklist. It draws on frameworks from my doctoral capstone (AIEIP), adapted for the FCCPS context. Everything here is a starting point for our colead discussion — I want your input on structure, scope, and FCCPS-specific adjustments before we finalize.

Deliverable 1: AI Tool / Data Risk Categories

Requirement: "Tool/data risk categories (plain language) + minimum requirements by category"

## Risk Tier Framework

Every AI tool used in FCCPS classrooms or operations would be classified into one of three tiers based on how it handles student data. Each tier triggers a different level of review and approval.

### Escalation Rules (applies to all tiers):

Integration / identity linkage escalator: Any tool that requires a student account or connects to FCCPS identity systems (SSO) or core platforms (SIS/LMS) is treated as Tier 3 for review, even if the vendor claims de-identification.

Consequential-use escalator: Any tool used to inform placement, grading, intervention, discipline, or SPED decisions is treated as Tier 3 for review (human-in-the-loop required).

Student artifacts caution: Student work artifacts (free-text writing, images, audio/video) can be identifying even without names. Tools receiving student artifacts should not be classified as Tier 1 unless artifacts are never transmitted to the vendor.

TIER 1 — LOW RISK: No Student Data What this means: The tool does not collect, store, or process student-identifiable information, and FCCPS does not transmit student-generated artifacts (free-text writing, images, audio/video) to the vendor. Typical use is staff-only, or student-facing use that does not require accounts/logins and does not send student content to the vendor. Examples: AI-powered lesson plan generators used only by teachers; AI image generators for creating classroom materials; grammar/style checkers used on teacher-authored content. Minimum Requirements: Staff completes Tier 1 affirmation ( - no student identifiers or student artifacts entered) - Tool is documented in department/school AI tool inventory - Basic review by department lead or instructional coach (purpose, settings, classroom-use constraints) Approval: Department/building-level approval. No DPA required.

TIER 2 — MODERATE RISK: De-Identified (Anonymized) or Aggregated Data What this means: The tool processes student work or interaction data in de-identified or aggregated form. FCCPS must be able to reasonably conclude that individual students cannot be identified from the data the vendor receives (including through student work artifacts). Examples: Classroom response/polling tools with anonymous mode; AI-assisted formative assessment tools using de-identified data; writing feedback tools where student names are stripped AND artifacts are handled under an approved de-identification approach. Minimum Requirements: - Vendor confirms de-identification/aggregation methodology in writing and contractually prohibits re-identification - Data Processing Agreement (DPA) reviewed and signed (including prohibition on advertising and AI model-training use of student data) - Data retention, deletion, and change-notice terms documented (vendor must specify how long data is held and notify FCCPS of material changes) - Annual review of vendor compliance - FERPA compliance verification Approval: District-level review (IT + curriculum). DPA required.

TIER 3 — HIGH RISK: Identifiable Student Data (including identity-linked systems) What this means: The tool collects, stores, or processes personally identifiable student information (PII), or can link data to a specific student. This includes tools where a student logs in with a school account, tools integrated with SIS/LMS/SSO, and tools that handle sensitive records. Examples: Adaptive learning platforms; AI tutoring systems with student accounts; any tool integrated with the SIS or LMS; AI tools used in IEP/504 planning or progress monitoring. Minimum Requirements: - Signed DPA with explicit data handling, retention, deletion, subprocessors, and prohibition on AI model-training use of student data (unless expressly authorized) Compliance verified for - FERPA, IDEA/Section 504/ADA (as applicable), COPPA (if applicable), and Virginia student data privacy law - For tools touching IEP/504 data: IDEA/504 compliance review + explicit parental/guardian consent, as required - Vendor security assessment (encryption, access controls, breach notification procedures, incident response) Right-sized impact/ - bias assessment for tools making recommendations about students (with disability-focused review when applicable) - Human-in-the-loop requirement for any consequential decisions (placement, grading, intervention, discipline) - Data deletion confirmation process when tool is discontinued - Semi-annual compliance review/audit for Tier 3 tools (focus on data practices + terms changes + incidents) Approval: District-level review (IT + curriculum + administration + legal). Full DPA + security review required. Pilot period recommended before broad deployment.

Special Considerations: Students with Disabilities and Other Sensitive Contexts AI tools used with students receiving SPED services require heightened scrutiny regardless of tier. In addition to FERPA, FCCPS must ensure AI practices align with IDEA, Section 504, and ADA expectations (as applicable). The following data categories are especially sensitive and trigger additional requirements: - IEP/504 plan data: Disability classifications, accommodations, modifications, and progress monitoring data. Assistive - technology usage patterns: Data from assistive tech tools may reveal disability-related information even when not explicitly labeled as such. - Behavioral and counseling-related data: Monitoring/behavior systems may amplify bias and drive high-stakes consequences. Student artifacts: Work samples can reveal disability-related information and can re-identify students. Additional requirement: Any Tier 2 or Tier 3 tool used with SPED populations must include an accessibility review (assistive tech compatibility, UDL alignment) and a disability-focused impact/bias review of outcomes.

## Deliverable 2: Procurement / Governance Decision Checklist

Requirement: "A short procurement/governance decision checklist (what must be true before adoption)"

This checklist is designed for any FCCPS staff member, administrator, or department considering adopting a new AI tool. It answers one question: Can we use this tool? Every item must be confirmed before the tool can move forward at its designated tier.

### Step 1: Classify the Tool

| Question |  | If YES → |  |
| --- | --- | --- | --- |
| Does the tool collect, store, or process any student-identifiable information (names, IDs, login data, work samples/student artifacts linked to students)? |  | Tier 3 — proceed to full review |  |
| Does the tool process student work or interaction data in de-identified (anonymized) or aggregated form? |  | Tier 2 — proceed to standard review |  |
| Does the tool have no contact with student data or student-generated artifacts at all? |  | Tier 1 — proceed to basic review |  |
| Will the tool be used with students receiving SPED services (IEP/504) or other sensitive contexts (e.g., counseling/health data)? | Add SPED/sensitive review layer (any tier) |

### Step 2: Verify Before Adoption

All items must be confirmed for the relevant tier. Items marked with ★ are non-negotiable across all tiers.

| What Must Be True Before Adoption | Tier 1 | Tier 2 | Tier 3 |
| --- | --- | --- | --- |
| ★ Tool is documented in FCCPS AI tool inventory | ✔ | ✔ | ✔ |
| ★ Staff member can articulate educational purpose and how the tool supports student learning | ✔ | ✔ | ✔ |
| ★ No student data is entered into the tool without appropriate authorization | ✔ | ✔ | ✔ |
| Vendor confirms anonymization methodology in writing | -- | ✔ | ✔ |
| Data Processing Agreement (DPA) reviewed and signed | -- | ✔ | ✔ |
| Data retention and deletion policy documented | -- | ✔ | ✔ |
| FERPA compliance verified | -- | ✔ | ✔ |
| Vendor security assessment completed (encryption, access controls, breach notification) | -- | -- | ✔ |
| Algorithmic bias assessment completed for any tool making recommendations about students | -- | -- | ✔ |
| Human-in-the-loop confirmed for consequential decisions (placement, grading, intervention) | -- | -- | ✔ |
| COPPA compliance verified (if tool is used by students under 13) | -- | -- | ✔ |
| Vendor terms prohibit use of student data for advertising or AI model training (unless expressly authorized) | -- | -- | ✔ |
| Pilot period completed with documented outcomes before broad deployment |  |  |  |
| SPED ADD-ON: IDEA compliance review + parental consent for IEP/504 data | If SPED | If SPED | If SPED |
| SPED ADD-ON: Accessibility review (assistive tech compatibility + UDL alignment) | If SPED | If SPED | If SPED |
| Vendor provides notice of material changes to data practices/terms and identifies subprocessors | -- | ✔ | ✔ |
| Tier 1 affirmation completed (settings + classroom-use constraints documented) | ✔ | -- | -- |

## Deliverable 3: Top Risks, Mitigations & Suggested Owners

Requirement: "Top risks + mitigations + suggested owners"

| RISK 1 Severity: HIGH | Unvetted AI Tools Processing Student Data Without Governance Without a structured approval process, teachers and staff may adopt AI tools that collect student PII without signed DPAs, creating FERPA violations and data exposure risk. Research shows no standardized regulations currently address AI-specific risks in K-12 education (DOE, 2023; Roschelle et al., 2024). |
| --- | --- |
| Mitigation | Implement the tiered approval process (Deliverable 1). Maintain a district-wide AI tool inventory. Require DPA review for all Tier 2/3 tools. Communicate clear policy that unauthorized tool adoption is prohibited. |
| Owner | IT Department (tool inventory + DPA management) + Building Administrators (enforcement) |

| RISK 2 Severity: HIGH | IEP/504 Data Exposure Through AI Tools SPED students’ sensitive diagnostic information, behavioral data, and learning accommodations are increasingly processed through AI systems that may lack adequate safeguards (Roschelle et al., 2024). IDEA requires protections beyond standard FERPA, and AI tools were not designed with these requirements in mind (Haque & Li, 2024). |
| --- | --- |
| Mitigation | SPED add-on review layer for any tool used with IEP/504 students. Explicit parental/guardian consent for AI processing of disability-related data. Prohibit sharing IEP/504 data with AI vendors without IDEA compliance review. Regular audits of AI tools used in SPED contexts. |
| Owner | SPED Director + IT Department (joint oversight) + Legal Counsel (IDEA compliance review) |

| RISK 3 Severity: MEDIUM | Algorithmic Bias in Student Assessment and Intervention AI systems misclassify students with disabilities from marginalized backgrounds at rates up to 32% higher than peers (Nguyen et al., 2023). AI-driven behavior monitoring may flag cultural behavioral differences as problematic (Maslej et al., 2023). This can reinforce historical overrepresentation of students of color in certain disability categories. |
| --- | --- |
| Mitigation | Require algorithmic bias assessment for all Tier 3 tools. Establish routine bias audits with specific focus on outcomes for students with intersecting marginalized identities. Human-in-the-loop requirement for all consequential decisions. Review disaggregated outcome data annually. |
| Owner | Curriculum & Instruction (bias audits) + SPED Director (disability-specific disability specific review) + Equity Office (intersectionality lens) |

| RISK 4 Severity: MEDIUM | Tool Proliferation Without Central Oversight Without a centralized inventory and approval process, individual teachers and departments may independently adopt AI tools, creating an unmanageable landscape of vendor relationships, inconsistent data practices, and compliance gaps that IT and administration cannot effectively monitor. |
| --- | --- |
| Mitigation | Maintain centralized AI tool inventory. Require all AI tool adoptions to go through tiered approval. Conduct annual audit of tools in use across the district. Establish clear communication channels for staff to request new tools. |
| Owner | IT Department (inventory + technical review) + Curriculum & Instruction (educational value assessment) |

| RISK 5 Severity: MEDIUM | Vendor Data Practices Beyond District Control AI vendors may change their data practices, terms of service, or AI model training approaches after adoption. Student data used to train commercial AI models without consent represents a significant and evolving privacy concern. |
| --- | --- |
| Mitigation | DPAs must include clauses prohibiting use of student data for model training. Require vendor notification of material changes to data practices. Establish annual vendor compliance review. Include data deletion requirements when contracts end. |
| Owner | IT Department + Legal Counsel (DPA management and enforcement) |

# Meeting 4 Readiness Checklist

From  John’s orientation email, each workstream needs these items ready for the convergence gate:

## 3 Non-Negotiable Constraints / Guardrails

| 1 | No AI tool may process identifiable student data without a signed Data Processing Agreement (including prohibition on advertising and AI model training use of student data unless expressly authorized) and completion of the tiered review process. |
| --- | --- |
| 2 | IEP/504 data must never be shared with AI vendors without explicit IDEA compliance review and parental/guardian consent. This is a federal requirement, not a policy choice. |
| 3 | All AI tools used for consequential decisions about students (placement, grading, intervention, behavioral assessment) must include human-in-the-loop oversight. AI recommendations inform — they do not decide. |

## 3 Decision Points / Tradeoffs for Committee Resolution

| # | Tradeoff | Notes |  |
| --- | --- | --- | --- |
| 1 | Approval speed vs. thoroughness | Balance teacher agility with compliance workload. |  |
| 2 | Approved list vs. criteria-based evaluation | Impacts curation effort and clarity for staff. |  |
| 3 | Compliance monitoring ownership | A) IT owns monitoring (technical focus) B) Curriculum & Instruction owns monitoring (instructional focus) C) Shared responsibility with clear RACI + defined cadence | Resource implications are significant. |
| 4 | District-provided tools vs. BYO (bring-your-own) tools | A) District-approved tools only B) Allow BYO for Tier 1 with guardrails + inventory requirement C) BYO allowed only in teacher-mediated mode; student-facing tools must be district-approved | Enforcement vs. innovation tradeoff. |
| 5 | Data minimization vs. personalization (instructional value) | A) Default to minimization; limit personalization features B) Allow Tier 3 personalization only with explicit educational rationale + pilot + monitoring C) Case-by-case with strict data elements list + sunset/review dates | Shapes tool capability and risk exposure. |

## Dependencies from Other Workstreams & FCCPS Staff

| What We Need | From Whom | Status |
| --- | --- | --- |
| Existing DPA templates and procurement workflows | FCCPS IT / Jerrod Anderson or Bethany Henderson | To request (IT/procurement owners) |
| Current AI tool inventory (what’s already in use) | FCCPS IT Department | To request (IT) |
| IT capacity for ongoing compliance monitoring | FCCPS IT Department | To confirm (IT) |
| Draft policy principles (from Meeting 3) | Full committee (Feb 20 output) | Pending Meeting 3 |
| Policy language alignment | Policy/Recommendation Drafting workstream (David Berol) | Coordinate with WS-Policy (in progress) |
| Virginia student data privacy law specifics | FCCPS Legal Counsel | Research in progress |

### Discussion Questions for Co-Lead Check-In

These are the key questions I’d like to work through in our first sync:

### On Structure & Scope

- Does the 3-tier model feel right for FCCPS, or should we adjust the categories? Are there tool types that don’t fit cleanly?

- Is the SPED add-on layer the right approach, or should SPED considerations be embedded directly into the tiers rather than as an overlay?

- The governance checklist is designed for staff and administrators. Is that the right audience, or do we also need a version for the procurement/IT team?

### On FCCPS-Specific Context

- Do you have contacts for FCCPS IT or procurement who can share existing DPA templates and the current tool landscape?

- Are there AI tools FCCPS is already using or evaluating that we should use as test cases for the checklist?

- What’s your sense of the committee’s appetite for the tradeoffs in the decision points? Are there other tradeoffs you think we’re missing?

### On Division of Labor

- My proposal: I continue drafting the checklist and risk tiers (building from my AIEIP work), and you review for technical accuracy and FCCPS-specific adjustments. Does that division work for you?

- Can we establish a weekly async rhythm?

1) Review cadence: Are there certain days that work best for you to review or collaborate? Please let me know your preferred days.

3. Are there specific sections you’d like to own or contribute to directly?

# Source: AIEIP Framework

The frameworks in this document draw from my doctoral capstone, the Artificial Intelligence Ethical Integration Program (AIEIP), developed at Simmons University. AIEIP establishes a comprehensive ethical and compliant framework for AI in special education settings, grounded in:

- DEIPAR Framework (Diversity, Equity, Intersectionality, Power, and Anti-Racism) — ensures that social justice remains central to AI governance. I understand we may not be able to display this with our current administration, and it can be adaptable with the FCCPS vision and mission.

- Diffusion of Innovations Theory — guiding phased implementation and adoption strategies

- FERPA, IDEA, and Section 504 compliance protocols — translated into actionable guidelines for educators

- AI Bias Audit methodology — routine assessment processes for identifying disparities in AI-driven decisions