# FCCPS AI Advisory Committee

# Workstream Development Summary & Lead Assignments

Version: v1.0
Last updated: 2026-02-18
Purpose: Summarize workstream development outputs and memorialize the assignment of workstream leads and co-leads (system-of-record snapshot for committee operations).

# 1. Overview

On 6 Feb 2026 (Meeting 2), the committee established eight workstreams to accelerate parallel development of research, policy drafting, and implementation recommendations. Workstreams are designed to converge through committee decision gates into a board-ready recommendations package.

This document captures:

- Workstream structure (IDs, names)

- Assigned leads/co-leads and known contributors

- Core responsibilities and first deliverables (“v1” outputs)

- Cross-workstream dependencies (high-level)

System of record note: The canonical, machine-readable registry and timeline remain the Workstreams Registry and Master Timeline files referenced below.

# 2. Workstreams and assignments (leads + co-leads)

| Workstream ID | Workstream | Lead | Co-lead | Contributors (as captured) |
| --- | --- | --- | --- | --- |
| WS-RSB | Research & Shared Baseline | Tom Colvin | Elizabeth Chua | Susan Nelson |
| WS-POL | Policy/Recommendation Drafting | David N. Berol | John Black | Tom Colvin; Jillian Burkley; Anubav Vasudevan |
| WS-CPX | Classroom Practice & Examples | Anubav Vasudevan | Susan Nelson | Adriana Palacios; Tom Sabo; Tina Beaty |
| WS-AIN | Assessment & Integrity | David N. Berol | Susan Nelson | John Black |
| WS-DPS | Data Privacy & Security | Jillian Marie Burkley | John Black | (none assigned) |
| WS-EQA | Equity & Access | Tom Sabo | Elizabeth Chua | Jillian Burkley; Adriana Palacios |
| WS-CCI | Communications & Community Input | Tina Beaty | Adriana Palacios | All members |
| WS-IPC | Implementation/PD & Change Adoption | Jillian Marie Burkley | Adriana Palacios | John Black |

# 3. Workstream outputs (first deliverables) and target checkpoints

These “v1” deliverables are the first convergence inputs into the committee’s drafting and decision flow.

| Deliverable ID | Title | Owner (lead) | Target checkpoint |
| --- | --- | --- | --- |
| D-RSB-1 | Shared Baseline Brief v1 | Tom Colvin | Pre-Meeting 3 inputs (Feb 2026) |
| D-POL-1 | Policy Skeleton v0 | David N. Berol | Meeting 4 (6 Mar) |
| D-CPX-1 | Scenario Bank v1 | Anubav Vasudevan | Meeting 4 (6 Mar) |
| D-AIN-1 | Attribution & Integrity Matrix v1 | David N. Berol | Meeting 4 (6 Mar) |
| D-DPS-1 | AI Tool Review Checklist v1 + Risk Tiers | Jillian Marie Burkley | Meeting 4 (6 Mar) |
| D-EQA-1 | Equity Impact Checklist v1 | Tom Sabo | Meeting 4 (6 Mar) |
| D-CCI-1 | Comms Pack v1 | Tina Beaty | Meeting 6 (10 Apr) |
| D-IPC-1 | Implementation Roadmap v1 | Jillian Marie Burkley | Meeting 6 (10 Apr) |

# 4. Workstream responsibilities (high-level)

## WS-RSB — Research & Shared Baseline

- Curate shared baseline on AI capabilities/limits, misconceptions, key terms, and classroom-reality examples

- Maintain annotated resource library + peer-district scan

- Produce concise briefs that reduce uncertainty and support decision-making

## WS-POL — Policy/Recommendation Drafting

- Own master outline and integrate inputs from all workstreams into coherent draft text

- Draft language options + decision points; maintain version history and decision log

- Package board-ready deliverables (written recommendations, appendices, executive summary)

## WS-CPX — Classroom Practice & Examples

- Collect and validate grade-banded classroom scenarios and use cases

- Translate policy into teacher-facing guidance, exemplars, prompts, and rubrics

- Identify usability constraints and PD needs; test guidance for clarity

## WS-AIN — Assessment & Integrity

- Define attribution expectations and acceptable AI assistance by grade and assessment type

- Recommend integrity safeguards (assessment design patterns, process evidence)

- Produce educator + student guidance for consistent implementation

## WS-DPS — Data Privacy & Security

- Define privacy/security requirements (minimization, retention, consent, records compliance)

- Create AI tool review checklist and risk-tiering aligned to governance/procurement

- Recommend vendor management expectations, guardrails, and incident considerations

## WS-EQA — Equity & Access

- Assess equity impacts (access gaps, accommodations, disability, language)

- Recommend accessibility standards and supports to mitigate unintended harm

- Define metrics and feedback loops to monitor disparities after implementation

## WS-CCI — Communications & Community Input

- Develop communications plan and key messages for families, students, staff

- Plan and synthesize community input (listening sessions, surveys, FAQs)

- Draft public-facing FAQs and guidance to build clarity and trust

## WS-IPC — Implementation/PD & Change Adoption

- Build implementation roadmap (phasing, pilots, milestones, owners, sequencing)

- Define success metrics, feedback loops, and review cadence

- Create adoption toolkits/templates (PD modules, checklists, exemplars)

# 5. Cross-workstream dependencies (what must align)

A small set of early alignments will prevent downstream rework:

- Definitions/assumptions and grade bands (WS-RSB + chair integration) must be stable enough to guide WS-CPX and WS-AIN outputs.

- Tool governance and privacy/security guardrails (WS-DPS) must inform recommendations structure (WS-POL) and operationalization (WS-IPC).

- Equity lens (WS-EQA) should be applied early to avoid retrofitting accessibility and access supports into late-stage drafts.

- Comms strategy (WS-CCI) should track evolving policy posture and be ready to accompany the near-final package.

# 6. Governance artifacts and where to find “source of truth”

Use the following project files as the authoritative references for process, schedule, and deliverables:

- Workstream assignments (Miro-captured) — narrative source

  - FCCPS AI Advisory Committee — Workstream assignments

- Workstreams Registry (System of Record) — canonical assignments + responsibilities + v1 deliverables

  - FCCPS AI Advisory Committee — Workstreams Registry (System of Record)

- Policy Recommendations Process and Timeline — committee process and milestones

  - FCCPS AI Advisory Committee — Policy Recommendations Process and Timeline

- Master Timeline (Workstream-aligned) — integrated schedule with decision gates and deliverables

  - FCCPS AI Advisory Committee — Master Timeline (Workstream-aligned)

- Deliverables Index — one-line tracker of deliverables, owners, due checkpoints

  - FCCPS AI Advisory Committee — Deliverables Index (v1.1 preferred)

- Decision & Change Log — prevent drift; record decisions and changes affecting downstream work

  - FCCPS AI Advisory Committee — Decision & Change Log

# 7. Next actions (recommended)

- Confirm WS-AIN co-lead assignment (or decide to keep unassigned with explicit support plan).

- Keep the Workstreams Registry and Master Timeline updated weekly (status, blockers, dependencies).

- Require that any change to scope, owners, deadlines, grade bands, or enforcement posture is recorded in the Decision & Change Log the same day.